PetPulse Agentic AI

Week 3 Plan — Admin Agent Replacement & Assistant Enhancements

| PREPARED July 25, 2026 | EXECUTION WEEK Mon Jul 27 – Fri Jul 31, 2026 | SPRINT Week 3 | STATUS Planned |
| --- | --- | --- | --- |

Objectives

Week 3 has two goals, run in parallel and delivered live by Friday:

1 · Replace the admin copilot: retire the GPT-era “AdminPulse AI” copilot on the admin dashboard and replace it with our own open-source agentic assistant that does not just summarize data but performs admin work — verifying professionals, moderating content, managing users — reliably and with full audit and confirmation.

2 · Enhance the assistant: extend the customer-facing assistant with emergency booking, concrete availability slots, automatic location ranking, self-service booking management, and multi-pet support.

Both build on the reliability-first architecture already in production: deterministic server rails for actions and data, with the LLM confined to intent extraction and phrasing. No paid APIs are introduced.

Current State — Why the Admin Copilot Must Be Replaced

Today the admin copilot lives in two endpoints (getAIInsights, askAIQuery in adminController.js, surfaced on pages/Admin.jsx). It reads and summarizes only — it cannot act — and has real correctness, scale, and privacy gaps:

| Area | Problem today | Target in Week 3 |
| --- | --- | --- |
| Capability | Read-only: cannot verify, ban, or moderate — the admin still does everything by hand. | Agentic tools that perform the action, gated by confirmation + audit. |
| Accuracy | askAIQuery dumps a LIMIT-100 snapshot into the prompt and lets the model filter — answers are wrong beyond 100 rows. | Deterministic SQL tools query the whole dataset; the model never filters data. |
| Privacy | Raw user/booking/post records are sent into the model prompt. | Records stay server-side; the model receives only intent and summaries. |
| Insights | getAIInsights mixes real counts with a hardcoded “15.4%” growth figure. | Every metric computed from the database; the model only phrases it. |
| Authorization | /admin/ai/* endpoints use requireAuth with no explicit admin-role guard. | Admin-role guard enforced on every AI endpoint and tool. |

Target Architecture — “AdminPulse Agent”

The admin agent mirrors the proven chatbot pattern (aiChatController + bookingFlow + tools), specialized for operations:

Deterministic rail: the model extracts intent and parameters; a coded rail runs the SQL and the writes.

Real tools: read tools (search users, analytics, bookings, moderation queue, pending verifications) and action tools (verify, ban, moderate, restore/delete, feature service) — each authorized to admin role.

Confirmation gate: destructive actions are proposed as a confirmation card and execute only on explicit admin “yes”.

Audit trail: every AI-performed action is written to the audit log, flagged as AI-initiated.

UI: streaming chat with structured result cards (user tables, booking lists, analytics, action confirmations), bilingual AR/EN.

Day-by-Day Plan

Monday, Jul 27 — Admin agent foundation & read tools (Track A)

| ID | Task & sub-tasks | Key files | Acceptance |
| --- | --- | --- | --- |
| A1 | Scaffold adminAgentController + adminTools factory mirroring the chatbot rail. Add and enforce an admin-role guard on all /admin/ai/* routes. | adminAgentController.js (new); adminTools.js (new); adminRoutes.js; authMiddleware.js | Non-admins receive 403; streaming agent endpoint responds with a session id. |
| A2 | Build deterministic READ tools: searchUsers (name/email/role/status, paginated), getUserDetail, getAnalytics (real revenue & growth), listBookings, getModerationQueue, listPendingVerifications. | adminTools.js; config/db.js | “show banned users”, “vets added this month”, “top bookings by price” return accurate whole-dataset results. |
| A3 | Rewrite POST /admin/ai/query into a query rail: model extracts {entity, filters}; code runs SQL. Remove the 100-row record dump from the prompt. | adminController.js (askAIQuery); adminTools.js | Answers correct beyond 100 rows; no raw records sent to the model; noticeably faster. |

Tuesday, Jul 28 — Agentic action tools, confirmation & audit (Track A)

| ID | Task & sub-tasks | Key files | Acceptance |
| --- | --- | --- | --- |
| A4 | Build ACTION tools reusing existing controller logic: verifyProfile (approve/reject), banUser / unbanUser (with reason), moderatePost (approve/remove), restorePost / deletePost, setServiceFeatured / price. | adminTools.js; adminController.js | Each tool performs the real DB change and returns a structured result. |
| A5 | Two-step confirmation gate: agent proposes a destructive action as a confirmation card and executes only on explicit “yes”. | adminAgentController.js; ChatMessageRenderer.jsx | Ban / delete / reject never auto-run; “cancel” aborts cleanly. |
| A6 | Audit every AI action to audit_logs (actor, action, target, reason, via_ai flag, time). Add via_ai column if missing. | migrations/add_ai_audit.sql (new); adminTools.js; adminController.js (getAuditLogs) | Audit view shows AI-performed actions distinctly with actor and reason. |

Wednesday, Jul 29 — Copilot UI, insights upgrade, bilingual (Track A)

| ID | Task & sub-tasks | Key files | Acceptance |
| --- | --- | --- | --- |
| A7 | Replace the insights/query widgets with a streaming chat panel using the structured block renderer (user-table, booking, analytics, action-confirmation cards). Rename GPT/Gemini → “AdminPulse Agent”. | pages/Admin.jsx; AdminAgentPanel.jsx (new); ChatMessageRenderer.jsx | Copilot streams; result and confirmation cards render and are clickable. |
| A8 | Upgrade getAIInsights to compute all aggregates deterministically (revenue, real week-over-week growth from timestamps, banned/queue counts); LLM only phrases them. | adminController.js (getAIInsights) | Every number traces to a query; the hardcoded growth figure is gone. |
| A9 | Bilingual admin agent: apply LANGUAGE_RULE + i18n to admin prompts and card chrome. | systemPrompts.js; adminAgentController.js; ChatMessageRenderer.jsx | Arabic questions answered in Arabic with localized cards. |

Thursday, Jul 30 — Customer assistant enhancements (Track B)

| ID | Task & sub-tasks | Key files | Acceptance |
| --- | --- | --- | --- |
| B1 | Emergency vets bypass the working-hours guard (is_emergency → 24/7 booking). | ai/tools.js (checkVetAvailability, bookAppointment) | Emergency vet books at 03:00; non-emergency still blocked. |
| B2 | Concrete availability slots: compute open slots from working_hours minus existing appointments; offer them as a card. | ai/tools.js (getOpenSlots, new); bookingFlow.js; ChatMessageRenderer.jsx | “book tomorrow” → agent offers real open times; tapping one books it. |
| B3 | Automatic geolocation ranking: with consent, capture browser lat/lng and rank vets by real distance without asking for an area. | components/Chatbot.jsx; aiChatController.js; ai/tools.js; bookingFlow.js | Consenting users get distance-ranked vets automatically; area fallback stays for others. |
| B4 | Manage bookings via chat: listMyAppointments, rescheduleAppointment, cancelAppointment — with confirmation and availability re-check. | ai/tools.js; bookingFlow.js; aiChatController.js | “reschedule my vet to 2pm” / “cancel my appointment” work with confirmation. |
| B5 | Multi-pet disambiguation before booking/triage when the user owns several pets. | bookingFlow.js; ai/tools.js | Multi-pet owner is asked which pet; single-pet flow unchanged. |

Friday, Jul 31 — Hardening, testing, deploy (Track C)

| ID | Task & sub-tasks | Key files | Acceptance |
| --- | --- | --- | --- |
| C1 | Observability: log admin tool calls, latency and outcomes to the AI observability tables; add admin-action counters. | ai observability module; adminAgentController.js | Admin AI actions and latency are queryable. |
| C2 | Rate limiting & input caps on all AI endpoints (per-admin and per-user). | middlewares/rateLimit.js (new); routes | Excess requests are throttled with a clear message. |
| C3 | End-to-end suites for the admin agent (read → action → confirm → audit) and the Track-B enhancements, run against the live deployment. | scripts/e2e_admin.mjs; scripts/e2e_assistant.mjs (new) | All scenarios pass on the deployed site. |
| C4 | Security review: admin-role authz on every tool, confirmation on destructive ops, audit completeness, no PII in prompts, secrets in env. | cross-cutting | Checklist signed off; no raw PII reaches the model. |
| C5 | Deploy to production (auto-deploy on push), live verification, and update docs with a Week 3 delivery report. | docs/ | Both agents live and verified; documentation updated. |

Weekly Timeline at a Glance

| Workstream | Mon 27 | Tue 28 | Wed 29 | Thu 30 | Fri 31 |
| --- | --- | --- | --- | --- | --- |
| A · Admin agent | A1–A3 | A4–A6 | A7–A9 | — | C-review |
| B · Assistant | — | — | — | B1–B5 | C-review |
| C · Hardening / deploy | — | — | — | — | C1–C5 |

Definition of Done

Admin agent: performs verify / ban / moderate through confirmed, audited tool calls; answers analytics questions from real, whole-dataset SQL; streams bilingual result cards; no GPT/Gemini references remain.

Assistant: emergency 24/7 booking, concrete slot suggestions, automatic geolocation ranking, and self-service reschedule/cancel all pass a live end-to-end test.

Safety: admin-role enforced everywhere, destructive actions gated and logged, no raw PII sent to the model, endpoints rate-limited.

Cost: running on the free open-source stack (Groq + Ollama + Vercel); no paid APIs added.

Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| An AI-triggered admin action causes irreversible damage. | Mandatory confirmation gate + audit log + admin-role authz on every write tool. |
| Open model filters admin data incorrectly. | Data comes from deterministic SQL tools; the model only extracts intent and phrases results. |
| PII exposure to the model. | Raw records never enter the prompt; tools return to the server and summarize. |
| Groq free-tier rate limits under demo load. | Default to Llama 3.1 8B, cache analytics, and throttle per admin/user. |
| Enhancement scope creep (Track B). | B1–B2 are committed; B3–B5 are stretch and drop first if Track A runs long. |

Dependencies & Assumptions

Reuse: the existing audit_logs table and admin controller logic are reused; only a via_ai flag migration is new.

Frontend: the structured block renderer is extended with admin card types — no new rendering framework.

Delivery: production continues to auto-deploy from the main branch on Vercel.

PetPulse Agentic AI · Week 3 Plan · Prepared July 25, 2026 · Execution Jul 27 – 31, 2026